## Bid Form
ELEVATOR MODERNIZATION SPECIFICATION
BID FORM SUMMARY EVENT 1501
|  |  |  | S&B Elevator |  | Platinum Standard |  | Schumacher |  | Twin Cities Elevator
A. Contract Price
Line # | Descrition | Unit | Estimated Quantity | Unit Price | Total price | Unit Price | Total price | Unit Price | Total price | Unit Price | Total price
1 | Elevators 3& 4Modernization - material | Project | 1 | 326800 | 326800 | 335420 | 335420 | 359620 | 359620 | 359186 | 359186
2 | Elevators 3&4 Modernization - Labor | Project | 1 | 172000 | 172000 | 200000 | 200000 | 232000 | 232000 | 339773 | 339773
3 | Warranty Maintenance | Month | 12 |  | 0 | 500 | 6000 | 680 | 8160 | 600 | 7200
4 | Total Bid Amount Please enter this amount on line response on supplier portal via www.stpaulbids.com |  |  | 498800 |  | 541420 |  | 599780 |  | 706159
Note: Owner reserves the right to accept/reject any or all line items. Quantities listed are an estimate; the unit bid price will be used in all instances for any quantity in the line item.
ESTIMATED SCHEDULE
| Descrition |  |  | how many weeks |  | how many weeks |  | how many weeks |  | how many weeks
1 | Shop drawings from date of award |  |  | 2025-02-28 |  | 2.5 |  | 7 |  | Eight Weeks
2 | Material delivery |  |  | 2025-06-23 |  | 16 |  | 12-15 post approvals |  | 28 Weeks from approvals
3 | Start on onsite mod: |  |  | 2025-07-01 |  | TBD by St Paul & Consultant |  | 12-16 post approvals |  | 28 Weeks from approvals
4 | Completion of first elevator |  |  | 2025-08-17 |  | 9.5 |  | 9 |  | 38 Weeks from approvals
5 | Completion of second elevator |  |  | 2025-10-03 |  | 9.5 |  | 9 |  | 48 Weeks from approvals
INTERIM MAINTENANCE Do not include Interim Maintenance in the base bid of the Modernization
|  | Unit | Quantity | Unit Price | Total Price | Unit Price | Total Price | Unit Price | Total Price | Unit Price | Total Price
1 | Elevators 3 Modernization | Month | 12 | 300 | 3600 | 300 | 3600 | 350 | 4200 | 300 | 3600
2 | Elevators 4 Modernization | Month | 12 | 300 | 3600 | 300 | 3600 | 350 | 4200 | 300 | 3600
3 | Total Interim Maintenance |  |  |  | 7200 |  | 7200 |  | 8400 |  | 7200
WARRANTY
| Description | Unit | Quantity | Unit Price | Total price | Unit Price | Total price | Unit Price | Total price | Unit Price | Total price
1 | Warranty Maintenance–12 months for Elevator 3 | month | 12 | 0 | 0 | 250 | 3000 | 340 | 4080 | 300 | 3600
2 | Warranty Maintenance–12 months for Elevator 4 | month | 12 | 0 | 0 | 250 | 3000 | 340 | 4080 | 300 | 3600
3 | Total Warranty Maintenance Cost |  |  |  | #REF! |  | 6000 |  | 8160 |  | 7200
NAME OF CONTRACTOR: |  |  |  | S&B Elevator Inc. - DBA Midwest Elevator & Drilling |  | Platinum Standard Elevator LLC |  | Schumacher Elevator |  | Metro Elevator
ADDRESS: |  |  |  | 5680 County Road 10 N |  | 2009 W Broadway Ave |  | 2995 Lone Oak Circle STE #1 |  | 1721 Mainstreet
[6 empty] | Suite 400 PMB 170 |  | Eagan, MN 55121 |  | Hopkins, MN 55343
Forest Lake, MN 55025
TELEPHONE / FAX NO |  |  |  | 952- 928-4202 |  | 763-689-8995 |  | 612-590-6001 |  | 952-932-9868
CELL PHONE |  |  |  | 612-718-1686 |  | 763-402-6530 |  | 612-590-6001 |  | 612-669-7414
EMAIL ADDRESS |  |  |  | Jake@mwemn.com |  | jake@platinumstandardelevator.com |  | joe.franczak@schumacherelevator.com |  | tara@metroelevatorinc.com
NAME |  |  |  | Jacob Schroeder |  | Jake Usher |  | Joe Franczak |  | Tara Bredeson
TITLE |  |  |  | President |  | Owner |  | Regional Vice President |  | Account Manager